**NIST Big Data Public Working Group (NBD-PWG)**

**NBD-PWD-2017/M0600**

Source:    NBD-PWG

Status:     Draft

Title:        NBD-PWG Meeting Agenda for Feb. 14, 2017

Author:   NBD-PWG Subgroup Co-Chairs

 Meeting logistics

Date/time: Feb. 14, 1:00PM – 3:00PM EDT

Web conferencing tool: <https://global.gotomeeting.com/join/790820565>

Audio: Use your microphone and speakers (VoIP) - a headset is recommended, or, call in using your telephone (US, long distance): +1 (646) 749-3122, access code/meeting ID: 790-820-565

**AGENDA**

1. **NBDIF Schedule**
   1. Review schedule deadlines
   2. NBD-PWG (<https://bigdatawg.nist.gov>) portal updates
2. **June 1 & 2 NBD-PWG Workshop**
   1. Review workshop flyer, program agenda, speakers, etc.
3. **Finalize Version 2 outlines and proposed preliminary content**
   1. Volume 1 Big Data Definitions – ready to post, Nancy
   2. Volume 2 Big Data Taxonomies – revised, Nancy
   3. Volume 3 Big Data Use Cases & Req. – waiting for new UC template V2 portal, Geoffrey, Piyush
   4. Volume 4 Big Data Security & Privacy, Arnab, Mark
   5. Volume 6 Big Data Reference Architecture, Dave
   6. Volume 7 Big Data Standards Roadmap – ready to post, Russell
   7. Volume 8 Big Data Ref. Arch. Interfaces – Gregor
   8. Volume 9 Big Data Adoption and Modernization – ready to post, Russell

**SCHEDULE**

1. **Jan 25:** Send all draft volumes (with at least TOC outline and proposed content) to Laurie for formatting
2. **Feb. 17:** Publish formatted draft documents online
3. **Feb 20:** Populate NIST portal with all draft NBDIF volumes, Use Case Template, and white paper template
4. **Feb 21:** Send invites to NBD-PWG reflector to invite new use cases with additional questions on security and Privacy
5. **Feb 21:** Announce June 1 & 2 workshop to public
6. **May 12:** Publish all draft volumes on the NIST portal for public review before workshop and send announcement to workshop participants and general public
7. **June 1&2:** Discuss and collect V2 comments
8. **June 3 – July 15:** NBD-PWG to resolve all comments and edits
9. **July 15:** Publish draft documents for official public comment period (45 days)
10. **Sept 1 – Sept 30:** NBD-PWG reviews and addresses public comments
11. **Oct 1 – Oct 30:** Perform NIST internal review
12. **Nov 1:** Publish final V2 of all volumes of NBDIF

**RESOURCES**

* **Volume 1 Draft:**

o   <https://docs.google.com/document/d/1kMu-EuFsJI6REnpNqshklvdoL4YLPAOy_sHCmvfNprc/edit?usp=sharing>:

* **Volume 2 Draft:**

o   <https://docs.google.com/document/d/1G8JTbcUwYE7uN82-TYYMfbDwJxCheooMsfktelXTWIc/edit?usp=sharing>

* **Volume 3 Draft:**

o   <https://docs.google.com/document/d/1SRaRPh_hOO_mYLy8qtG-kmsckbAhNIXnbGJ0SJBR6HU/edit?usp=sharing>

* **Volume 4 Safety Levels spreadsheet:**

o   <https://drive.google.com/file/d/0BzQlzFarkgmGMm9JbkY5Z1JmV2c/view?usp=sharing>:

         **Volume 6 Draft**

o   <https://docs.google.com/document/d/1Tol4tKxo-xugIjVyjfm9GSJpbNRFB3AFXQ4unKJjW0w/edit?usp=sharing>

         **Volume 6 RA diagrams**

o   <https://docs.google.com/presentation/d/1CXRUgjoe5PaU-vNk8-aESBuHwGwS6lD_iLKd6lrIa3c/edit?usp=sharing>

* **Volume 7 Draft**

o   <https://docs.google.com/document/d/1glX0vwWLgxcpxf_E60t0FGrOcoD3c9h5O7DIDJTp8Ng/edit?usp=sharing>

         **Volume 8 Draft**

o   Draft will be posted online by 1/31/17

         **Volume 9 Draft**

o   Draft will be posted online by 1/31/17